## Sheet1
ID | Date | Task | Member
1 | 2023-03-10 | Proposal | all team members
2 | 2023-03-13 | Home page html | Malak Abdulakher
3 | 2023-03-14 | Home page CSS | Malak Abdulakher
4 | 2023-03-14 | Navbar | Malak Abdulakher
5 | 2023-03-17 | Subpages | Malak Mohamed, Hager Hesham, Mariam Abdou, Tsneam Ahmed
6 | 2023-03-26 | Card generator js code | Malak Mohamed
7 | 2023-03-30 | signup | Malak Abdulakher
8 | 2023-03-30 | login | Malak Abdulakher
9 | 2023-03-31 | validation js | Malak Mohamed
10 | 2023-04-19 | SRS | all team members
11 | 2023-05-06 | creating django server | Malak Mohamed
12 | 2023-05-17 | products database | Tsneam Ahmed
13 | 2023-05-17 | Registeration | Mariam Abdou
14 | 2023-05-19 | orderforms database | Hager Hesham
15 | 2023-05-19 | SDD | all team members